## Instructions
INDUSTRY ACADEMIA COMMUNITY
DOMAIN NAME: | ARTIFICIAL INTELLIGENCE
INTERN NAME: | EDGAR PINTO
DOCUMENT NAME: | TEST PLAN
CREATED ON: | 2024-08-12
Purpose of Document
A Test Plan is a detailed document that describes the test strategy, objectives, schedule, estimation, deliverables, and resources required to perform testing for a software product.
Test Plan helps us determine the effort needed to validate the quality of the application under test.
The test plan serves as a blueprint to conduct software testing activities as a defined process, which is minutely monitored and controlled by the test manager
INSTRUCTIONS:
1. Text in Italics are instructions for completing the document
2. Text in orange is just for reference and should be deleted before submitting the document
3. Comments are added to some of the cells, please read the comments to better understand the terms
4. All fields must be duly filled

## TEST PLAN
TEST PLAN
PROJECT NAME | ARTIFICIAL INTELLIGENCE CHATBOT
PROJECT ID | IP -4356
INTERN NAME | EDGAR PINTO
PROJECT MANAGER | Harshada Topale
INTRODUCTION
(Brief introduction of the test strategies, process, workflow and methodologies used for the project)
This test plan outlines the strategies, workflows, and methodologies for testing the AI-powered chatbot developed for seamless communication across multiple platforms (Facebook, Instagram, LinkedIn, WhatsApp, and SMS). The goal is to ensure the chatbot meets functional and non-functional requirements, with both text and voice interaction capabilities. We will follow systematic testing to identify issues, validate functionality, and ensure a high-quality user experience.
SCOPE
IN SCOPE (Defines the features, functional or non-functional requirements of the software that will be tested)
Testing chatbot integration with Facebook, Instagram, LinkedIn, WhatsApp, and SMS. Verification of both text and voice interaction capabilities. Accuracy of the chatbot's responses (target: 95% accuracy). Performance testing to ensure it can handle high user traffic and meet the requirement of reducing human intervention by 70%. Validation of user data privacy compliance and secure data handling.
OUT SCOPE (Defines the features, functional or non-functional requirements of the software that will NOT be tested)
Custom mobile application development. In-depth analytics beyond basic performance reports.
QUALITY OBJECTIVE
(Mention the overall objective that you plan to achieve without your testing)
The main objectives of the testing are to ensure: The chatbot meets both functional and non-functional requirements. Voice and text interactions function seamlessly across platforms. The chatbot responds with 95% accuracy. Performance issues such as slowdowns or API bottlenecks are identified and addressed. User data is handled securely, complying with all privacy regulations. Bugs/issues are identified and resolved before the final deployment.
ROLES AND RESPONSIBILITIES
(Detail description of the Roles and responsibilities of different team members)
QA Analyst: To perform manual and automated testing of the chatbot features. Test Manager: To oversee the test strategy, manage the testing team, and ensure deadlines are met. Developers: To implement fixes for identified bugs and issues. Configuration Manager: To manage the environments used for testing. Installation Team: To deploy the chatbot to various platforms for user testing. Project Manager (Harshada Topale): To coordinate the entire testing process, track progress, and ensure quality objectives are met.
TEST METHODOLOGY
OVERVIEW (Mention the reason of adopting a particular test methodology for the project)
The test methodology chosen for this project is Agile, allowing us to adapt and test in iterative cycles based on evolving chatbot functionality. Given the complexity of integration with multiple platforms, Agile ensures continuous feedback, faster issue resolution, and enhanced flexibility in making necessary improvements.
TEST LEVELS (Define the Types of Testing to be executed on the Application Under Test (AUT))
Unit Testing: To ensure individual components (e.g., text and voice interaction) function as expected. Integration Testing: To validate the smooth integration of the chatbot across Facebook, Instagram, LinkedIn, WhatsApp, and SMS. System Testing: Complete end-to-end testing of chatbot functionality, performance, and compliance with the scope. User Acceptance Testing (UAT): Testing with a group of users to validate that the chatbot meets business needs and provides a satisfactory user experience.
BUG TRIAGE (Define resolution of each bug, prioritize bugs and determine a schedule for all “To Be Fixed Bugs’)
Resolution of Bugs: Define clear criteria for bug resolution based on severity and priority. For example: Critical bugs (blocking functionality) must be fixed immediately or within the next sprint. High-priority bugs should be resolved before the end of the testing phase. Medium and low-priority bugs will be scheduled for resolution in future sprints or releases.Bug Prioritization: Prioritize bugs based on their impact on user experience and system performance. Involve stakeholders in the prioritization process to align with business goals. Schedule for Fixes: Create a bug-fixing schedule aligned with the project timeline. Ensure that critical bugs are resolved in time for the User Acceptance Testing (UAT) phase.
TEST COMPLETENESS (Define the criteria that will deem your testing complete)
Criteria for Completeness: 100% test coverage for all identified test cases. All manual and automated test cases have been executed. All critical and high-priority bugs have been resolved. All known bugs have been documented, and a plan is in place for their resolution in future releases. Test results meet the performance and accuracy goals, such as the chatbot achieving 95% response accuracy.
TEST DELIVERABLES
(Mention all the Test Artifacts that will be delivered during different phases of the testing lifecycle)
Test Artifacts: Test Plan document outlining the testing scope, strategy, and objectives. Detailed Test Cases covering all functionalities (text and voice interaction). Requirement Traceability Matrix (RTM) to ensure all requirements are tested. Bug Reports with detailed descriptions, steps to reproduce, and severity levels. Test Strategy document outlining the overall approach to testing. Test Metrics report summarizing test coverage, defects found, and testing progress. Final Test Summary Report with conclusions and recommendations. Customer Sign-Off document indicating that testing has been completed to the customer’s satisfaction.
RESOURCE AND ENVIRONMENT NEEDS
TESTING TOOLS
Tools Required: Requirements Tracking Tool: JIRA or similar for tracking requirements and test cases. Bug Tracking Tool: JIRA or Bugzilla for tracking and managing bugs. Automation Tools: Selenium, JUnit for automating test cases. Other Tools: Postman for API testing, and any other tools required for backend and frontend testing.
TEST ENVIRONMENT (Minimum hardware requirements that will be used to test the Application)
Hardware Requirements: Cloud server with sufficient CPU, memory, and storage capacity. High-speed internet connection for reliable API calls and interaction handling. Software Requirements: Windows 8 and above, or equivalent for development and testing. Office 2013 and above for documentation and communication. MS Exchange for email integration if needed. Secure cloud environment with Node.js, React, and GPT-4.0 API integration.
ADDITIONAL COMMENTS
Any additional information relevant to testing, such as: Dependencies on third-party APIs. Constraints regarding testing timelines. Risk mitigation strategies for potential issues.
TEST PLAN
ITEMS TO TEST | TEST DESCRIPTION | TEST START DATE | TEST END DATE | RESPONSIBLE PERSON | STATUS | COMMENTS
Text Interaction Engine | Ensure individual components of the chatbot's text interaction engine are functioning as expected. | 2024-08-12 | 2024-08-13 | Himanshu | PASSED | Test engine logic and response accuracy.
Backend System Integration | Ensure smooth integration between the chatbot and its backend system for managing FAQs and interactions. | 2024-08-13 | 2024-08-14 | Sahil | PASSED | Test data flow and response retrieval times.
Data Handling and Compliance | Verify that the chatbot correctly handles, stores, and retrieves data, adhering to privacy and security standards. | 2024-08-14 | 2024-08-15 | Edgar | PASSED | Focus on GDPR and other relevant regulations.
Load Testing | Assess the chatbot's performance under various user loads to ensure stability and responsiveness. | 2024-08-15 | 2024-08-16 | Seemran | PASSED | Simulate peak traffic conditions.
Voice Recognition Module | Validate that the voice recognition module accurately interprets and processes user voice commands | 2024-08-17 | 2024-08-18 | Himanshu | PENDING | Focus on recognizing different accents.
WhatsApp API Integration | Validate successful communication between the chatbot and WhatsApp API, ensuring message reliability | 2024-09-19 | 2024-08-20 | Edgar | PENDING | Include edge cases like API rate limits.
Facebook API Integration | Confirm that the chatbot integrates seamlessly with the Facebook API, handling all interactions appropriately. | 2024-08-21 | 2024-08-23 | Sahil | PENDING | Test on both personal and business accounts.
Real-World Scenarios | Test the chatbot with real users to validate its effectiveness in providing accurate and timely responses. | 2024-08-23 | 2024-08-24 | Seemran | PASSED | Gather user feedback and satisfaction scores.
All Core Functionalities | Verify that new updates or bug fixes haven't negatively impacted existing functionalities. | 2024-08-24 | 2024-08-27 | edgar,sahil | PASSED | Retest all major functionalities post-fix.
Identified Bugs | Track, prioritize, and verify the fixes for all bugs identified during previous testing phases. | 2024-08-24 | 2024-08-27 | Himanshu,seemran | PASSED | Continuous triage based on severity and impact.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: To determine scope, you must – > Precise customer requirement > Project Budget > Product Specification > Skills & talent of your test team
Note on C24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: The objective of the testing is finding as many software defects as possible; ensure that the software under test is bug free before release. To define the test objectives, you should do 2 following steps: > List all the software features (functionality, performance, GUI…) which may need to test. > Define the target or the goal of the test based on above features
Note on C40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: A Testing Type is a standard test procedure that gives an expected test outcome. all Testing Types are aimed at achieving one common goal “Early detection of all the defects before releasing the product to the customer. There are tons of Testing Types for testing software product. Your team cannot have enough efforts to handle all kind of testing. As Test Manager, you must set priority of the Testing Types > Which Testing Types should be focused for web application testing? > Which Testing Types should be ignored for saving cost? The commonly used testing types are: 1. Unit Testing 2. API Testing 3. Integration Testing 4. System Testing 5. Install/Uninstall Testing 6. Agile Testing You need to decide based on your project scope, time and cost the testing type(s) required for your project
Note on C48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Test Criteria is a standard or rule on which a test procedure or test judgment can be based. There’re 2 types of test criteria as following Suspension Criteria Specify the critical suspension criteria for a test. If the suspension criteria are met during testing, the active test cycle will be suspended until the criteria are resolved. Exit Criteria It specifies the criteria that denote a successful completion of a test phase. The exit criteria are the targeted results of the test and are necessary before proceeding to the next phase of development. Example: 95% of all critical test cases must pass.